## Cover
#VALUE! | TEST PLAN
Project Name | Test CellphoneS |  |  | Reviewer | Team
Project Code |  |  |  | Review date
Creator | Nguyễn Thị Xuân Hoa |  |  | Approver | Trần Thị Thanh Nga
Version | v1.0 |  |  | Approval Date
Record of change
Effective Date | Version | Change Item | A, D, M | Change description
31/12/2019 | v1.0 | Initial
Index
Sheet Name | Description |  |  |  | Note
Cover | Title page
Test Policy | - General policy for Test process, Test case design, Test Data - List of requirements to Test/not Test - Exit criteria for testing - Suspension criteria and Resumption requirements
Test Management | - Test scope - Deliverable - Management method - Risk - Assumption - Training plan
Test Strategy | Identification of Test level, Test types, Test environments, Test data and Enviroment for test
Master Schedule | Introduction and Define team, master schedule for testing
Appendix | - Description and detailed definition of Test level, types and techniques - List of Terminologies and definition/explanation |  |  |  | For Reference only
Reference Document
Name |  |  |  | Version | Note
SRS_Group13_v1.0 |  |  |  | v1.0

## Test Policy
Test Policy
Test process policy
Description of policies of testing process.
| # | Description | Responsibility | Note
| 1 | Xác định và phân tích các yêu cầu chức năng liên quan đến chức năng lịch sử mua hàng, bao gồm hiển thị các đơn hàng trước đây, chi tiết đơn hàng và các tùy chọn lọc. | Requirement Analysis
| 2 | Xây dựng kế hoạch kiểm tra nêu rõ các mục tiêu, phạm vi, nguồn lực cần thiết, lịch trình và các thành viên trong nhóm chịu trách nhiệm. | Test Planning
| 3 | Tạo các trường hợp thử nghiệm bao gồm các tình huống như xem các đơn đặt hàng trước đây, chức năng sắp xếp, xác minh hủy và trả lại cũng như xử lý lỗi. | Test Case Design
| 4 | Thực thi các trường hợp thử nghiệm trên nhiều trình duyệt khác nhau (Chrome, Edge) và các thiết bị (máy tính để bàn, thiết bị di động). | Test Execution
| 5 | Tài liệu đã xác định vấn đề kèm theo các bước chi tiết để tái tạo, mức độ nghiêm trọng và ảnh chụp màn hình nếu có. | Defect Reporting
| 6 | Xác minh cách giải quyết các sự cố được báo cáo và đảm bảo rằng các bản sửa lỗi không gây ra sự cố mới. | Retesting
Test case design policy
Description of policies of test case design.
| # | Items | Note
| 1 | Người dùng truy cập thành công lịch sử mua hàng của họ và xem chi tiết đơn hàng chính xác.
| 2 | Kiểm tra các chức năng, dữ liệu trong lịch sử mua hàng
| 3 | Đánh giá giao diện người dùng để dễ điều hướng và rõ ràng thông tin hiển thị.
Quality metric
Description of target
| # | Items | Target | Note
| 1 | Đảm bảo việc kiểm tra bao gồm tất cả các khía cạnh của lịch sử mua hàng, bao gồm truy xuất đơn hàng, lọc và hiển thị chính xác trạng thái đơn hàng | Functional Coverage
| 2 | Xác minh rằng dữ liệu người dùng trong lịch sử mua hàng được bảo mật và chỉ những người dùng được ủy quyền mới có thể truy cập được. | Security Coverage
| 3 | Kiểm tra khả năng phản hồi của chức năng trong điều kiện tải bình thường và cao điểm, đảm bảo đáp ứng thời gian phản hồi chấp nhận được. | Performance Coverage
Pass/Fail Criteria
The conditions that the testing must satisfy to end test.
| # | Criteria | Priority | Note
| 1 | 80% trường hợp kiểm thử đã hoàn thành/tổng số trường hợp kiểm thử (độ bao phủ kiểm thử > 80%) |  | Thực hiện các trường hợp thử nghiệm có mức ưu tiên cao nhất trước, sau đó tăng dần.
| 2 | Kiểm tra mức độ bao phủ thành công >= 80%
| 3 | Phần mềm đúng với SRS
Suspension Criteria and Resumption Requirements
Specify when to pause in a series of tests and requirements for resumption of test activities.
| # | Suspension Criteria | Note
| 1 | When a defect is introduced that cannot allow any further testing
| 2 | A specific holiday shuts down both development and testing (Tet Holiday)
| 3 | If there is any network, hardware problem in the organisation, we can suspend testing
| 4 | If we got more pending requests with the development team
| # | Resumption Requirements | Note
| 1 | When the particular issue has been addressed and solved

## Test Management
Test Management
Test Scope
Listing of test items in test process.
# | Items | Description |  | Responsibility | Note
1 | Create test plan |  |  | Nguyễn Thị Xuân Hoa
2 | Create test design |  |  | Nguyễn Thị Xuân Hoa
3 | Create test cases |  |  | Nguyễn Thị Xuân Hoa
4 | Create test data |  |  | Nguyễn Thị Xuân Hoa
5 | Thực thi system test |  |  | Nguyễn Thị Xuân Hoa
6 | Defects list |  |  | Nguyễn Thị Xuân Hoa
7 | Create test report |  |  | Nguyễn Thị Xuân Hoa
Deliverables
Listing of documents will be delivered of test process.
# | Deliverables | Delivered date | Delivered by | Delivered to | Note
1 | Test plan | 27-11-2023 | Test leader | Nguyễn Thị Xuân Hoa
2 | Test cases | 27-11-2023 | Test leader | Nguyễn Thị Xuân Hoa
3 | Defect logs | 27-11-2023 | Test leader | Nguyễn Thị Xuân Hoa
4 | Test report | 27-11-2023 | Test leader | Nguyễn Thị Xuân Hoa
Management method
Describe the management method of test process.
# | Object | Method |  |  | Note
1 | Issue Tracking Tools | Trello
2 | Communication Channels | Zalo, Messeger
Risks
Listing of all risks of test process and action to mitigate the risk and do if risk become reality.
# | Condition |  | Mitigation |  | Contingency
1 | Team members lack experience in software testing domain |  | Plan training course to skill up your members |  | 1. Connect with a training organization 2. Attend mandatory training 3. Quality test
2 | The development team improved the code which led to the testing process being paused |  | Accept this risk |  | Contact the development team
3 | The project schedule is too tight; it's hard to complete this project on time |  | Set test priority for each test case and execute the test case with the highest priority |  | 1. Determine the priority for each test case 2. Set priority for each test case 3. Follow the priority level
4 | Members misunderstood the request |  | Organize to review and analyze requirements to member before starting the testing process |  | 1. Hold a meeting 2. Review required 3. Inspections
5 | Employees reduce working performance after Tet holiday |  | Accept this risk |  | OT to keep up with the schedule
Assumption
Listing of all assumption of test process.
# | Type | Description
1
2
Training Plan
Plan training for test team.
# | Training Topic | Description |  | Responsibility | Start Date | End Date

## Test Strategy
Test Strategy
Test Objective:
To ensure doesn’t contain serious bugs before release to customer, to confirm that the system has met the requirements
Test stages & techniques
Listing of all test stages of project, and test techniques must be done of every test stages.
Test stage | Unit testing | Integration Testing | System Testing | User acceptance testing
Test techniques
White box testing | x |  | x
Black box testing |  | x | x | x
Responsibility | Developer | Tester | Tester | Tester
Requirements to be tested
Listing of what is to be tested from the USERS viewpoint of what the system does.
Feature/Function |  | Document which is testing base on |  |  | Note
Chức năng [Lịch sử mua hàng] của hệ thống CellphoneS được mô tả trong tài liệu SRS, các chức năng được kiểm tra theo thứ tự ưu tiên từ cao đến thấp (ưu tiên cao nhất được kiểm tra trước) |  | SRS_Group13_v1.0
Test environment
Listing of environments use in test process.
Type | Environment |  |  |  | Note
Hardware | Laptop, Smartphone |  |  |  | Standard Fsoft
OS | Window 10 64bit Android 13.0
Software | Chrome version 119.0.6045.200 (Official Build) (64-bit) Edge 121.0.2248.1 dev (64-bit)
Database | MS SQL
Browser | Edge, Chrome
Network configured | LAN Wifi

## Master Schedule
Master Schedule
Project Team
Listing of all workers join the testing process
# | Worker / Doer | Position | Responsibilities
1 | 20130038_Nguyễn Thị Xuân Hoa | Member | Đọc và phân tích tài liệu, test design, test case, thực thi các test case, logs bug cho chức năng [Lịch sử mua hàng].
Master Schedule
# | Item | Start Date | End Date
1 | Create test plan | 27/11/2023 | 30/11/2023
2 | Create test design | 2023-01-12 | 2023-03-12
3 | Create test case | 2023-04-12 | 2023-09-12
4 | Execute test and log bugs | 2023-10-12 | 20/12/2023
5 | Evaluting exit criteria & Test report | 21/12/2023 | 24/12/2023
6 | Review | 25/12/2023 | 26/12/2023
| Task | Start day from 9/12/2019 | Duration
| Create test plan | 0 | 3
| Create test design | 3 | 2
| Create test case | 5 | 5
| Execute test and log bugs | 10 | 10
| Evaluting exit criteria & Test report | 20 | 3
| Review | 23 | 1
Detail Schedule
Liên kết

## Details Schedule
# | Item | Responsibilities | November |  |  |  | December | [48 empty] | January
|  |  | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
1 | Create test plan | Nguyễn Thị Xuân Hoa | bar: November 27 to November 30
2 | Create test design | bar: December 1 to December 3
2.1 | Chức năng lịch sử đơn hàng | Nguyễn Thị Xuân Hoa | bar: December 1 to December 3
3 | Create test case | bar: December 4 to December 9
3.1 | Chức năng lịch sử đơn hàng | Nguyễn Thị Xuân Hoa | bar: December 4 to December 9
4 | Execute test and logs bug | bar: December 10 to December 20
4.1 | Chức năng lịch sử đơn hàng | Nguyễn Thị Xuân Hoa | bar: December 10 to December 20
5 | Evaluting exit criteria & Test report | Team | bar: December 21 to December 24
6 | Review | Team | bar: December 25 to December 26

## Appendix
Appendix
Term definition
# | Term | Definition/explanation
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
17
Glossary
#
1
1
2
3
4
#
4
5
6
7
8
9
10
11
12
13
14